## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
Faults in my computer or system | A fault in my computer or a complete break could possibly happen, and would lead to loss of the local repository and an inability to carry on the project. | I back up my computer regularly and also push to Git regularly so that if something were to happen I would always be able to access a recent version. | To make sure my data and dev environment is secure in case of an accident. | Unlikely | Major
Corrupted file | The file which stores all the documents and code for the project has a possibility to become corrupted due to many unavoidable reasons. | Backing up to Github, including backing up the schema so that the database is not lost either. If the database were corrupted for a working version of this application it would be much higher impact. | To minimise the risks of data corruption by backing up often. | Unlikely | Minor
Loss of internet during the project | Losing signal for the internet is a possibility, and has happened previously during my time at QA. Would lead to inability to push to Git/to access online repository. | Always keep a local repository so code is accessible even if online. | To ensure that time is not wasted on internet issues and to keep both online and local repositorys. | Likely | Minor
Bugs/unthrown exceptions in the code | Bugs and unthrown exceptions could make it to the final submission version of the project. | Thorough testing aiming for as much coverage as possible, as well as using the project often to ensure that it is performing SQL database operations correctly. | To be able to have functional and high quality code in the final version. Risk depends on the severity of the bug. | Likely | Hazardous
Project not being ready by the deadline | If the project is not complete by the deadline, it could miss testing or not be fully functional. | To ensure that I plan my sprints appropriately so that my time is used as effectively as possible to avoid missing the deadline. Also, work first on a MVP before adding extra features. | To ensure that I use my time as effectively as possible to avoid missing the deadline. | Unlikely | Hazardous